MATHEMATICS,
UNDERSTOOD

PROJECT BIBLE  |  VERSION 1.0

Foundational Charter, Editorial System,
and Verification Protocol

━━━━━━━━━━━━━━━━━━━━━━━━━━━━

From intuition to symbols. From symbols to understanding.
From understanding to discovery.

A comprehensive self-study mathematics series
from foundational numeracy to advanced mathematics,
with connected applications in science.

FOUNDATIONAL DRAFT  •  19 OCTOBER 2026

Working title; subject to naming and trademark review

# Contents

1. Mission and promise

2. Audience, scope, and boundaries

3. Non-negotiable principles

4. The Intuition-to-Formalism Bridge (IFB)

5. Chapter and exercise standards

6. Curriculum architecture

7. Science companion series

8. Mathematical and factual integrity system

9. Source and copyright policy

10. Review gates and defect severity

11. Manuscript workflow and version control

12. Roles and decision rights

13. Pilot plan and acceptance criteria

14. Risks and mitigations

15. Decisions intentionally left open

16. First actions

17. References

18. Appendices and reusable templates

How to use this document Treat this as the working constitution for the series. It is Version 1.0 and should be updated through a recorded decision process. This is a foundational draft, not a claim that the teaching method has already been experimentally validated.

# 1. Mission and promise

## 1.1 Mission

Create a rigorous, welcoming, self-contained mathematics education series that helps learners build usable intuition, precise formal knowledge, procedural fluency, mathematical reasoning, and the ability to apply ideas independently—regardless of their educational background.

The project must teach more than how to reproduce a procedure. Learners should increasingly understand what mathematical objects represent, why relationships have the structure they do, what assumptions a method requires, how a result follows, and where that result can be used.

## 1.2 Intended learner outcome

After studying a concept, a learner should be able to do as many of the following as are appropriate to that concept:

Explain the idea in their own words without relying on a memorized phrase.

Interpret its symbols, quantities, relationships, assumptions, and units where relevant.

Move between useful verbal, numerical, graphical, geometric, and symbolic representations.

Reconstruct or justify the central rule or derivation instead of merely recalling it.

Calculate accurately and select an appropriate method without being prompted with a formula.

Identify boundary conditions, counterexamples, exceptions, or limitations.

Apply the concept to a changed or unfamiliar problem.

Connect it to earlier mathematics and, where relevant, to a scientific model.

Not every objective applies identically to every topic. Abstract proof, for example, requires forms of reasoning that cannot always be grounded in a physical analogy. The promise is a supported path to rigor, not the elimination of all difficulty.

## 1.3 The project promise

Core promise Help learners read, reason with, and create mathematics—not merely manipulate mathematical symbols.

The project does not claim that mathematics is literally a natural language, that every formula has a simple everyday translation, or that a single teaching method has already been proven superior across all ages and branches of mathematics. Those are claims to investigate, not assumptions to advertise.

## 1.4 How success will be judged

Success is not page count, visual polish, learner praise alone, or the number of examples generated. The principal indicators are:

Mathematical and scientific correctness.

Clear and faithful explanations.

Independent usability.

Accurate execution and justification.

Transfer to unfamiliar problems.

Delayed retention where it can be assessed.

Consistency and traceability across the full collection.

This balanced view is informed by the National Research Council’s account of mathematical proficiency, which treats conceptual understanding, procedural fluency, strategic competence, adaptive reasoning, and productive disposition as connected strands rather than independent goals [1]. The report is a useful framework, not proof that this exact project design will succeed; our method must be tested.

# 2. Audience, scope, and boundaries

## 2.1 Primary audience

The intended audience is broad: complete beginners, school learners, adult returners, university students, independent learners, and advanced readers who want a clearer conceptual account of topics they already use.

The curriculum must not assume one uniform route through every chapter. It will provide:

Explicit prerequisites and diagnostic checks.

Multiple entry points where prior knowledge differs.

Short repair sections for common prerequisite gaps.

Clear links to prerequisite chapters.

Advanced extensions without making them mandatory for every reader.

## 2.2 Scope of the core series

The core mathematics collection is intended to progress from basic quantities and arithmetic through algebra, geometry, functions, trigonometry, logic, calculus, linear algebra, probability and statistics, differential equations, and selected advanced topics such as real analysis, abstract algebra, complex analysis, topology, and measure theory.

The detailed list, order, volume boundaries, and depth are not frozen in v1.0. They will be established by a prerequisite and concept-dependency map before full book production. Some topics require parallel pathways rather than one linear route.

## 2.3 Scope of the science companion series

A connected application collection will show how mathematical ideas are used in physics, chemistry, biology, and broader scientific modeling. Applications will be tied to core prerequisites and will distinguish among:

Mathematical identities or theorems.

Assumptions of a physical or scientific model.

Empirical laws and approximations.

Numerical or symbolic calculations.

Interpretations that are helpful pedagogically but are not themselves mathematical proofs.

The science books will not be used to smuggle unexplained mathematics into the core curriculum. When required mathematics is introduced in an application chapter, the chapter must either teach the required idea adequately or point to a suitable core treatment and provide a short, correct refresher.

## 2.4 Out of scope for the initial phase

Draft the entire collection in one pass.

Promise a fixed number of volumes or publication date.

Claim measured learning benefits without comparative evidence.

Treat an AI-generated answer or citation as verified merely because it sounds plausible.

Require learners to use paid software or a specific device to complete the core books.

Make visual effects, gamification, or analogies more important than mathematical truth.

# 3. Non-negotiable principles

## 3.1 Intuition before formalism, where appropriate

Begin with a question, pattern, problem, observation, or useful mental model. Introduce formal terminology and symbolic structure after the learner has a foothold. The sequence may need to change for certain topics, but the chapter must make the reason for that change clear.

## 3.2 Rigor without compromise

Intuition supplements formal mathematics; it does not replace definitions, valid derivation, proof, exact conditions, or correct calculation. Every claim must be stated at the level of precision appropriate to the chapter.

## 3.3 Multiple representations with explicit connections

Use verbal descriptions, number lines, diagrams, tables, graphs, physical models, symbolic expressions, and code when each genuinely helps. Do not decorate the page with a representation that adds no understanding. Explain how representations connect and where they cease to be equivalent.

## 3.4 Every operation is interpreted in context

The books must explain why operations appear in particular expressions. They must not force one simplistic translation onto a symbol. Multiplication may express scaling, area, a product of quantities, composition, or a different structure; division may express a ratio, rate, inverse operation, or normalization. The correct interpretation depends on definitions and context.

## 3.5 Derivations explain decisions

Worked derivations should tell learners why a relation is introduced, why a transformation is allowed, what assumptions are being used, and how the result can be checked. Algebraic steps should not be skipped simply because an experienced author finds them obvious.

## 3.6 Understanding must transfer

Learners need tasks that change the numbers, representation, assumptions, or context. Familiar-example imitation is not sufficient evidence of mastery.

## 3.7 Independent learning is a design constraint

Each chapter must include enough orientation, explanation, practice, feedback, and solution support for a learner to study alone. Do not rely on a teacher being present to fill in missing logic.

## 3.8 Accessibility without dilution

Use plain language where it is accurate. Define unavoidable technical vocabulary. Avoid unnecessary jargon, but introduce the correct term when learners need it. “Easy to read” must never mean “less precise.”

## 3.9 Scientific honesty

State the scope and limits of analogies and models. Distinguish exact results from approximations, empirical observations, conjectures, and interpretations. Do not imply a causal or physical explanation where the mathematics alone does not establish one.

## 3.10 Learnability over spectacle

Every figure, sidebar, analogy, story, interaction, or visual element must support understanding, memory, reasoning, or application. Engagement is valuable only when it serves learning.

# 4. The Intuition-to-Formalism Bridge (IFB)

The working teaching method is named the Intuition-to-Formalism Bridge (IFB). It is an editorial framework to be tested and refined, not a claim of a newly validated theory of learning.

## 4.1 The usual sequence

1.  Question: What are we trying to describe, understand, calculate, or prove?

2.  Intuition: Build an initial mental model with a familiar situation, pattern, thought experiment, or concrete example.

3.  Representations: Connect appropriate verbal, numerical, graphical, geometric, and symbolic views.

4.  Precise language: Introduce quantities, definitions, notation, and technical terms.

5.  Formal structure: State the mathematical relationship, theorem, procedure, or definition exactly.

6.  Justification or derivation: Establish why the result follows, with assumptions and permitted steps made explicit.

7.  Guided practice: Solve examples while explaining choices and checks.

8.  Independent practice: Progress from execution to explanation, construction, proof, and transfer.

9.  Boundary and connections: Examine exceptions, limiting cases, counterexamples, related concepts, and applications.

10.  Retrieval and return: Revisit the concept in cumulative reviews and later chapters.

This order is flexible, but missing stages must be a deliberate decision, not an oversight. For example, an advanced proof may require definitions before a useful intuition emerges. In that case, the book should help readers build intuition alongside the formal work instead of fabricating a misleading analogy.

## 4.2 The operation-interpretation protocol

What are the objects and quantities?

What relationship is claimed?

Why is the selected operation appropriate in this context?

Which definitions, laws, assumptions, or modeling choices justify it?

What does the expression imply when one quantity changes?

What are the units, domain restrictions, sign behavior, and limiting cases, where applicable?

Is there a counterexample to an oversimplified verbal interpretation?

## 4.3 Illustrative example: electrostatic interaction energy

U(r) = k q₁q₂ / r,     k = 1 / (4π ε₀)

For two point charges in the electrostatic setting, with zero potential energy chosen at infinite separation, the interaction energy is given by the expression above.

A sound intuitive treatment should derive the structure rather than assign arbitrary meanings to the symbols. The potential created by the first point charge is proportional to q₁/r; the potential energy of the second charge in that potential is q₂ times the potential. This leads to the product q₁q₂ and the inverse distance dependence. The sign depends on the charge signs and the chosen reference convention. The model and its assumptions must be stated.

For the dipole example, the learner then sums the four pairwise charge interactions with their appropriate signs and separations. If a distant-dipole approximation is introduced, the chapter must explain the geometry, approximation conditions, and orientation dependence. It must not suggest that the simplified pair-charge expression alone automatically gives every dipole interaction result.

This example is a prototype of the teaching method, not yet an approved chapter.

# 5. Chapter and exercise standards

## 5.1 Standard chapter architecture

Prerequisites: What the reader should already know; short diagnostic questions.

Learning outcomes: Observable capabilities, not vague statements such as “understand the topic.”

Motivating question: The reason the concept is useful or mathematically necessary.

Intuitive entry point: A clear mental model, example, pattern, or puzzle.

Representation bridge: Connections among words, pictures, numerical examples, graphs, and symbols.

Definitions and notation: Precise meanings, domains, assumptions, and conventions.

Derivation, explanation, or proof: A transparent account of why the central result holds.

Worked examples: From straightforward to subtle, including a deliberately contrasted example where useful.

Common misconceptions: Explain why tempting mistakes fail and how to detect them.

Practice ladder: Recognition, execution, explanation, construction or proof, and transfer.

Boundary cases and connections: Limits, exceptions, counterexamples, and links to earlier or later chapters.

Summary and retrieval prompts: Key relations, questions without notes, and cumulative-review pointers.

Hints and solutions: Sufficient reasoning for independent learning.

Verification notes: Internal evidence and checking records retained in the project repository.

## 5.2 Exercise standards

Exercises should be varied and purposeful. A chapter should generally include:

Concept identification and interpretation.

Routine fluency problems.

Explanation and error diagnosis.

Derivation, construction, or proof where appropriate.

Mixed practice in which the learner chooses the method.

At least a small number of transfer tasks.

Cumulative questions that bring back important earlier concepts.

No arbitrary percentage distribution is frozen at this stage; it should vary by topic. A proof chapter and an introductory arithmetic chapter require different exercise mixes.

## 5.3 Solution standards

A final answer alone is insufficient for an exercise designed to teach reasoning. Worked solutions should include the key decisions, assumptions, transformations, checks, and interpretation. For challenging questions, staged hints should be available before the full solution. Deliberate ambiguity, if part of the exercise, must be explained in the solution.

## 5.4 Memory and review

Use retrieval practice, cumulative review, and spaced revisiting as practical design tools. Intervals should be adjustable rather than presented as a universal schedule. The National Research Council’s proficiency framework supports combining conceptual understanding with procedural fluency and reasoning [1]; it does not dictate one exact review algorithm. The pilot should measure whether the review features help actual readers.

# 6. Curriculum architecture

## 6.1 Planned progression

| Pathway | Provisional coverage |
| --- | --- |
| Foundations | Quantities, number sense, arithmetic, place value, fractions, ratios, proportion, powers, roots, estimation, and measurement. |
| Mathematical language | Variables, expressions, equations, inequalities, functions, graphs, coordinate geometry, and algebraic transformations. |
| Shape and periodicity | Geometry, trigonometry, spatial reasoning, vectors, and geometric proof. |
| Reasoning | Logic, sets, quantifiers, proof methods, counterexamples, and induction, introduced gradually and consolidated explicitly. |
| University foundations | Calculus, linear algebra, discrete mathematics, probability, statistics, and mathematical modeling. |
| Applied and advanced routes | Multivariable calculus, differential equations, numerical methods, optimization, real analysis, abstract algebra, complex analysis, topology, measure theory, and selected specialized areas. |

This is not yet a table of contents. The master curriculum map must decide prerequisites, overlaps, depth, and placement. Some subjects, such as logic, proof, vectors, and functions, should recur before their dedicated advanced treatments.

## 6.2 Dependency map rules

Every major topic must have a record of:

Concept ID and canonical name.

Learner-facing explanation of the concept.

Prerequisite concepts.

Learning outcomes.

First introduction and later revisits.

Definitions, theorems, formulas, and methods that belong to it.

Common misconceptions and known fragile transitions.

Exercise types and mastery evidence.

Relevant science applications.

Sources and verification status.

A concept cannot be placed in a chapter only because it makes the local story convenient. Its prerequisites must be checked, and necessary prerequisite gaps must be handled explicitly.

## 6.3 Flexible entry

Readers should be able to use diagnostic questions and prerequisite links to enter at an appropriate point. A diagnostic must point to specific concepts needing repair, rather than labeling a learner globally as “bad at math.”

## 6.4 Progression and review

Important ideas may reappear at increasing levels of abstraction. Each return should add something: a more general definition, a proof, a new representation, a broader class of problems, or a new application. Repetition without additional purpose should be removed.

# 7. Science companion series

## 7.1 Purpose

The companion collection shows how mathematics is used to describe, infer, predict, and model aspects of the world. It should make scientific applications more understandable without presenting mathematical manipulation as a substitute for science.

## 7.2 Initial application domains

Mathematical language of nature: Units, dimensions, scaling, estimation, graphs, measurement, uncertainty, and modeling.

Physics: Mechanics, energy, momentum, oscillations, electricity, magnetism, waves, and later mathematical physics.

Chemistry: Stoichiometry, concentration, logarithms and pH, kinetics, equilibrium, thermodynamics, spectroscopy, and quantum chemistry.

Living systems: Growth models, probability, genetics, networks, epidemiology, statistics, and dynamical models.

Advanced interdisciplinary modeling: Differential equations, linear algebra, probability, optimization, numerical methods, and other topics as prerequisite depth permits.

This structure is illustrative. Actual books should be scoped only after the core dependency map identifies what mathematics learners will have available.

## 7.3 Application chapter requirements

Each application chapter must identify its mathematical prerequisites; define variables and units; state assumptions; distinguish idealized from measured quantities; show how the mathematics enters the model; interpret the result; examine at least one limitation or sensitivity where appropriate; and link back to the core book.

## 7.4 Keep categories distinct

Editorial review must distinguish a mathematical theorem from a physical law, an empirical correlation, a modeling assumption, a numerical estimate, and an intuitive interpretation. A correct algebraic derivation cannot by itself establish that a scientific model accurately describes reality.

# 8. Mathematical and factual integrity system

## 8.1 Governing rule

No important claim is considered verified merely because an AI system wrote it, repeated it, or generated a citation for it. NIST’s Generative AI Profile identifies risks associated with generative AI and presents lifecycle-oriented risk-management guidance [2]. This project applies that general principle to mathematical and scientific educational publishing.

## 8.2 Verification lanes

| Content type | Required check | What the check does not prove |
| --- | --- | --- |
| Algebraic identity or simplification | Independent symbolic or numerical checks plus a human derivation review | That a formula was appropriate for the original problem |
| Numerical example or answer key | Independently recompute; automated tests for repeated exercise families | That the method or assumptions are correct |
| Proof or theorem | Check definitions, quantifiers, assumptions, logical steps, counterexamples, and relevant cases; use formal proof checking where justified | That exposition is clear or the theorem is the intended one |
| Units and physical dimensions | Dimensional analysis and unit consistency | That a physical model is empirically valid |
| Scientific model | Authoritative source check and subject-matter review; verify conditions and limitations | That every result is universal beyond the model’s domain |
| Intuition or analogy | Seek counterexamples, edge cases, alternate interpretations, and learner feedback | That the analogy is a proof |
| Historical or factual claim | Primary or authoritative source where possible; record exact support | That the source has been interpreted correctly without review |
| Citation or quotation | Open the source and verify the exact relevant passage, edition, page or section | That the source supports more than the verified claim |
| Learner-facing explanation | Independent pedagogical critique and pilot testing | That one successful reader represents every audience |

## 8.3 Mathematical checking toolkit

Hand derivation: Essential for understanding the logic and assumptions.

Computer algebra: A tool such as SymPy can test symbolic transformations and calculations within the tested domain.

Numerical testing: Substitute carefully chosen values, including boundary and edge cases.

Unit and dimensional checks: Useful for detecting inconsistencies in physical formulas.

Code-based exercise tests: Recompute answers over many generated inputs when exercises have reliable programmatic specifications.

Formal proof checking: Consider Lean and its mathematical ecosystem for selected proof-heavy material when the formalization cost is justified [6].

A tool’s output is evidence only within its scope. A symbolic algebra system can confirm an equivalence under assumptions but does not validate the origin of a model. Numerical samples can detect errors but do not prove a universal identity. A proof assistant checks a formal statement and proof, so both must match the intended mathematics.

## 8.4 Claim ledger

For every substantial chapter, keep a ledger containing claim ID, exact claim, type, assumptions, derivation or evidence, source and precise locator where applicable, verification methods, reviewer, status, date, and unresolved issues. Claims that are routine and directly derived may need a lighter record than high-risk scientific or advanced claims, but every chapter requires a documented review.

## 8.5 AI drafting rules

AI may help draft prose, devise examples, generate candidate exercises, identify missing cases, suggest source leads, and create automated checks. It must not be treated as the final verifier. The workflow should preserve source provenance, use task-specific tests, and keep a human review route. Evaluation should be repeatable, specific to the task, and updated as errors are found, consistent with general evaluation guidance for variable AI outputs [3].

The process must not fabricate references, quotations, page numbers, theorem names, proof results, or claimed review outcomes. If the evidence cannot be checked, mark the content UNVERIFIED and do not publish it as established fact.

## 8.6 Independence of review

A second pass by the same model is useful as a challenge exercise, but it is not independent evidence. High-risk claims should be checked through genuinely different routes: manual derivation, computational verification, trusted sources, another qualified reviewer, or formalization where appropriate.

# 9. Source and copyright policy

## 9.1 Source hierarchy

Original papers, authoritative standards, official mathematical documentation, or primary records for claims that require them.

Established textbooks and university-published materials for explanations, definitions, standard derivations, and curricular context.

Reputable review articles and professional educational resources for synthesis.

General web pages as discovery aids, not as final authority for important technical claims.

A source being reputable does not guarantee that every statement in it applies to our context. Check the relevant passage and scope.

## 9.2 Record exact support

For each sourced claim, preserve title, author or organization, edition or version, publication date where relevant, stable URL or DOI, exact page/section/figure where available, access date for changing webpages, and the claim supported. Distinguish a source used for verification from one used only to discover another source.

## 9.3 Originality and permissions

Create original explanations, exercises, examples, diagrams, and chapter structure. Cite sources for facts and intellectual context, but do not use citation as permission to copy protected prose, illustrations, or substantial problem sets. Track licences and permissions before reusing material. Any direct quotation must be necessary, attributed, and checked against the applicable copyright and permissions policy.

## 9.4 Reference management

Use a persistent bibliography and stable source IDs. Zotero or a comparable reference manager can store source metadata and PDFs; the project repository should hold a source-to-claim index so citations remain meaningful when manuscripts move between tools.

# 10. Review gates and defect severity

A chapter moves through explicit gates. A green status means the defined checks were completed and recorded; it does not mean that errors are metaphysically impossible.

## 10.1 Production gates

| Gate | Release requirement |
| --- | --- |
| A — Scope approved | Learning outcomes, prerequisites, topic boundaries, and sources are identified. |
| B — Draft complete | All required sections and exercises exist; incomplete sections are visibly marked. |
| C — Mathematical verification | Derivations, calculations, assumptions, symbols, units, and answer keys checked. |
| D — Pedagogical review | Intuition, representations, transitions, misconceptions, practice, and independent usability reviewed. |
| E — Scientific/reference review | Scientific claims, source support, licenses, and citations checked as applicable. |
| F — Reader test | A sample learner can navigate the chapter and complete the targeted tasks; issues are logged. |
| G — Editorial freeze | Corrections are incorporated, cross-references checked, change record updated, and publication files rendered and inspected. |

A chapter should not skip a gate silently. If a gate is not applicable, record the reason.

## 10.2 Severity levels

| Severity | Meaning | Required response |
| --- | --- | --- |
| S0 — Critical | False theorem, materially wrong scientific claim, dangerous misconception, or error invalidating a major learning outcome. | Block release; correct and recheck all dependent content. |
| S1 — Major | Incorrect derivation, wrong answer key, omitted essential assumption, misleading analogy, or broken prerequisite preventing learning. | Block chapter approval until corrected. |
| S2 — Moderate | Ambiguous wording, incomplete explanation, weak example, missing useful edge case, or inconsistent notation that can mislead. | Resolve before publication or explicitly document an approved deferral. |
| S3 — Minor | Typographical, formatting, or stylistic issue that does not change meaning. | Correct during editorial review; batch safe low-risk edits. |

Any correction to a mathematical statement, derivation, scientific assumption, or answer key triggers a regression check of related examples, exercises, solutions, and cross-references.

# 11. Manuscript workflow and version control

## 11.1 Single source of truth

Keep the project in a persistent, version-controlled repository. The exact tool can be chosen for ease of use, but the repository must have clear versions, backups, and a directory structure that separates the editorial rules, curriculum map, manuscripts, source records, tests, review reports, diagrams, and release files.

Suggested layout:

mathematics-understood/
  PROJECT_BIBLE.md
  curriculum/
    concept_map.csv
    prerequisite_graph.md
    learning_outcomes.csv
  standards/
    chapter_template.md
    notation_guide.md
    verification_checklist.md
    citation_policy.md
  books/
    core/
      volume-01/
        chapter-01.md
        claims.csv
        exercises.csv
        tests/
    science/
  sources/
    bibliography.bib
    source_to_claims.csv
  reviews/
    open_issues.csv
    decision_log.md
  assets/
    diagrams/
  releases/

The layout is a recommendation; it can be simplified at the pilot stage. The key requirement is durable traceability, not a particular tool.

## 11.2 Draft workflow

1.  Create a chapter brief from the approved curriculum map.

2.  Assemble source packets and record assumptions.

3.  Draft the explanation, derivation, examples, exercises, and answer key.

4.  Run the relevant mathematical, numerical, dimensional, citation, and consistency checks.

5.  Conduct a separate challenge review focused on counterexamples, missing cases, and misleading interpretations.

6.  Obtain the required human or domain review.

7.  Test the chapter with readers and log the outcomes.

8.  Resolve defects and rerun regression checks.

9.  Render the final manuscript and inspect every page and mathematical figure.

10.  Record the release version and its verification status.

## 11.3 Change management

Maintain a decision log for meaningful changes to curriculum, notation, teaching rules, or scope. When a concept changes, identify dependent chapters, exercises, science applications, and tests. Do not assume a local edit has no downstream effect.

## 11.4 Manuscript status labels

Use explicit labels such as OUTLINE, DRAFT, MATH CHECK PENDING, SOURCE CHECK PENDING, EXTERNAL REVIEW PENDING, PILOT PENDING, APPROVED FOR LAYOUT, and RELEASED. Never describe a draft as verified, peer-reviewed, or publication-ready if the corresponding gate has not been completed.

# 12. Roles and decision rights

## 12.1 AI drafting and analysis role

The AI assistant may propose structures, draft text, derive candidate solutions, generate exercises, run available tools, identify uncertain claims, organize sources, and revise material from feedback. It must state uncertainty, retain review records, and never certify its own unaudited output as error-free.

## 12.2 Project lead role

The project lead controls the vision, scope, priorities, and final publishing decisions. The project lead need not personally master every branch of mathematics but must ensure that appropriate external expertise is obtained before high-risk advanced material is released.

## 12.3 Expert review role

A qualified reviewer checks the mathematics and/or science within their remit. A reviewer should be told what they are being asked to verify; an informal glance is not equivalent to a full mathematical or pedagogical review.

## 12.4 Reader testing role

Pilot readers reveal where the explanation fails in practice. Their feedback informs revision, but reader preference does not override mathematical correctness.

## 12.5 Approval rule

AI-generated content alone cannot authorize a chapter for release. Final release requires the applicable documented checks and the project lead’s approval. Advanced mathematics and scientific modeling require specialist review where the potential cost of error is high.

# 13. Pilot plan and acceptance criteria

## 13.1 Pilot selection

Foundational: Fractions, ratios, and proportional reasoning. This tests entry-level clarity, visual representations, arithmetic accuracy, prerequisite diagnosis, and independent solution support.

Advanced application: Electrostatic interaction energy leading into the pairwise construction of a dipole interaction. This tests mathematical precision, physical assumptions, sign conventions, derivation transparency, approximation boundaries, and the ability to move between intuitive explanation and formal calculation.

The prototypes need not be full market-ready books. They should be substantial enough to exercise the chapter template, verification ledger, exercises, source policy, and reader testing.

## 13.2 Pilot cycle

1.  Define the target learner profile and outcomes for each prototype.

2.  Create the concept and prerequisite records.

3.  Assemble a small, trustworthy reference set.

4.  Produce the first draft and complete all internal checks.

5.  Ask at least one appropriate independent reviewer to examine high-risk content; use additional reviewers when the topic warrants it.

6.  Test with readers whose prior knowledge fits the intended use.

7.  Observe whether they can explain, calculate, justify, and transfer the target concepts.

8.  Log defects by severity, revise, and retest the material affected.

9.  Decide whether to refine the method, accept it for wider production, or redesign parts of it.

## 13.3 Pilot acceptance criteria

All stated outcomes map to explanations and assessment tasks.

Prerequisites and assumptions are explicit.

All central derivations and worked answers have documented checks.

No unresolved S0 or S1 defects remain.

Important sources and quotations have been verified.

Scientific models and approximations state their scope and limitations.

A reader can use the book without a teacher to understand instructions, attempt practice, and check solutions.

Transfer questions test something not reproduced verbatim in the explanation.

Learner feedback and known weaknesses are recorded.

The project lead accepts any remaining S2/S3 issues or records a concrete resolution plan before release.

The pilot is a feasibility and quality test, not a controlled demonstration that the method is superior to conventional books. Any comparative learning claim would require a suitably designed study with appropriate measures and sample selection.

# 14. Risks and mitigations

| Risk | Mitigation |
| --- | --- |
| Plausible but false AI-generated explanation | Claim ledger, independent derivation, computational checks, external review, and explicit uncertainty labels |
| Citation invented or not actually supportive | Open every source used for important claims; record exact page/section and claim mapping |
| Intuitive analogy becomes a misconception | Test counterexamples, mark limits, and transition explicitly to formal definitions |
| Curriculum has gaps or jumps | Dependency graph, prerequisite checks, and pilot feedback |
| Exercise answer key contains errors | Independently recompute, add test cases, and run regression checks after corrections |
| Science model is presented as universal | Record domain, conditions, approximations, and domain-expert review |
| Scope becomes too large to manage | Prioritize a pilot, freeze the core standards, use incremental releases, and avoid premature volume-count promises |
| Chapters become inconsistent | Shared notation guide, term list, canonical concept IDs, and change log |
| Reader appreciates the style but does not learn | Assess explanations, independent problem-solving, transfer, and delayed retrieval—not satisfaction alone |
| Copyright or attribution problem | Write original material, check licence terms, maintain permissions records, and review borrowed assets |
| Context lost between writing sessions | Maintain the Project Bible, curriculum repository, chapter status, source records, and decision log outside the chat |

# 15. Decisions intentionally left open

Final project and series names; trademark and domain checks.

Exact number and size of volumes.

Detailed curriculum order and depth of each advanced topic.

Primary publishing format, page design, and release strategy.

Which materials will be openly licensed and under what terms.

Exact learner-testing design and whether a formal comparative study is feasible.

Which chapters warrant formal proof assistant work.

Budget, paid expert review, external editing, and publication timeline.

Whether supplementary digital tools or interactive exercises are worth the cost.

The project should prefer reversible decisions early and reserve expensive commitments until the pilot clarifies them.

# 16. First actions

1.  Approve or amend this Project Bible. Record every change in a decision log.

2.  Build the Master Curriculum Map. Define concept IDs, prerequisites, learning outcomes, first introduction, later revisits, applications, and verification needs.

3.  Create the two pilot chapter briefs. One foundational and one advanced scientific application.

4.  Build the claim ledger and QA checklist. Use them before drafting large amounts of prose.

5.  Draft and verify the pilots. Do not expand the collection until the production process has been exercised end to end.

Next planned deliverable Master Curriculum Map v0.1 — concept inventory, prerequisite graph, learning outcomes, and cross-links to science applications.

The immediate next deliverable after this document is the Master Curriculum Map, beginning with a prerequisite graph, not a polished table of contents. That graph will drive book boundaries and show where the science companions depend on core mathematics.

# 17. References

[1] National Research Council. Adding It Up: Helping Children Learn Mathematics. National Academies Press, 2001. Chapter 4, “The Strands of Mathematical Proficiency.” DOI: https://doi.org/10.17226/9822. https://www.nationalacademies.org/read/9822/chapter/6

[2] Autio, C., Schwartz, R., Dunietz, J., Jain, S., Stanley, M., Tabassi, E., and Hall, P. Artificial Intelligence Risk Management Framework: Generative Artificial Intelligence Profile. NIST AI 600-1, National Institute of Standards and Technology, 2024; see the official record for updates. DOI: https://doi.org/10.6028/NIST.AI.600-1. https://nvlpubs.nist.gov/nistpubs/ai/NIST.AI.600-1.pdf

[3] OpenAI. “Evaluation Best Practices.” OpenAI API Documentation. https://developers.openai.com/api/docs/guides/evaluation-best-practices/

[4] Institute of Education Sciences / What Works Clearinghouse. “Assisting Students Struggling with Mathematics: Intervention in the Elementary Grades.” Practice Guide and related resources on instructional language and representations. https://ies.ed.gov/ncee/wwc/PracticeGuide/26

[5] Institute of Education Sciences. “Module 2: Representations.” Resource describing concrete, semi-concrete, and abstract representations for mathematics instruction. https://ies.ed.gov/ncee/rel/math-support-grades-3-6/teach-pd-module2-rep

[6] Lean Language. “The Lean Language Reference” and “Learn Lean.” Official documentation for the Lean theorem prover and learning resources. https://lean-lang.org/doc/reference/latest/ and https://lean-lang.org/learn/

Reference-use note: These sources inform parts of the general framework; they do not certify this project design. Claims in future chapters require source verification specific to their topic. Web references last checked for this Project Bible on 19 October 2026.

# 18. Appendices and reusable templates

## Appendix A — Chapter brief template

| Field | Record |
| --- | --- |
| Chapter ID |  |
| Working title |  |
| Target learner / entry point |  |
| Learning outcomes |  |
| Prerequisite concept IDs |  |
| Concept IDs introduced |  |
| Definitions and notation |  |
| Central claims / theorems / formulas |  |
| Intuitive entry point |  |
| Representations to use and why |  |
| Derivation / proof plan |  |
| Worked-example plan |  |
| Common misconceptions and counterexamples |  |
| Exercise ladder and transfer question |  |
| Science applications |  |
| Reference packet |  |
| Verification plan |  |
| Required reviewer(s) |  |
| Acceptance criteria |  |
| Open issues |  |
| Status |  |

## Appendix B — Claim ledger template

| Field | Record |
| --- | --- |
| Claim ID |  |
| Exact statement |  |
| Claim type: definition / derivation / theorem / numerical result / scientific model / sourced fact / analogy |  |
| Assumptions and domain |  |
| Source and exact locator (if applicable) |  |
| Derivation or evidence |  |
| Independent check method |  |
| Test cases / edge cases |  |
| Reviewer and date |  |
| Status: unverified / checked / reviewed / approved |  |
| Known limits or unresolved questions |  |
| Dependent sections, exercises, or applications |  |

## Appendix C — Chapter release checklist

Learning outcomes are observable and assessed.

Prerequisites and entry points are explicit.

All symbols and terms are defined before reliance on them.

Each major intuitive interpretation is compatible with the formal mathematics.

Analogy boundaries and counterexamples are supplied when needed.

Derivations have no unexplained or invalid transitions.

Assumptions, domains, units, sign conventions, and approximations are checked where applicable.

Worked examples and every published answer key were independently checked.

Exercises cover explanation, procedure, reasoning, and transfer where appropriate.

Sources are real, opened, correctly represented, and linked to the claims they support.

Copyright and licence checks are complete for reused material.

Scientific content has appropriate domain review.

No unresolved S0 or S1 defects remain.

Relevant regression checks have passed after the final edit.

Reader testing is complete or its absence is explicitly disclosed.

Final layout, equations, figures, tables, and page breaks have been visually inspected.

Version, status, reviewers, and unresolved lower-severity issues are recorded.

## Appendix D — Defect report template

| Field | Record |
| --- | --- |
| Issue ID |  |
| Chapter / location |  |
| Severity: S0 / S1 / S2 / S3 |  |
| Observed problem |  |
| Why it matters |  |
| Evidence or counterexample |  |
| Proposed correction |  |
| Affected claims, examples, exercises, or chapters |  |
| Regression checks required |  |
| Owner |  |
| Status |  |
| Resolution and date |  |

## Appendix E — Decision log template

| Field | Record |
| --- | --- |
| Decision ID and date |  |
| Question |  |
| Options considered |  |
| Decision |  |
| Rationale and evidence |  |
| Consequences |  |
| Affected documents / concept IDs |  |
| Revisit condition (if any) |  |